## ALL
PROJECT NAME* | LEAD AGENCY | PROJECT DESCRIPTION | PROJECT COST | NEPA | [15 empty] | NMFS EFH CONSULTATION |  |  |  |  | NMFS ESA CONSULTATION | [6 empty] | USFWS ESA CONSULTATION | [6 empty] | SECTION 106 |  |  |  |  | USACE SECTION 10/404 |  |  |  |  | BLM RIGHT-OF-WAY |  |  |  |  | USFS SPECIAL USE PERMIT |  |  |  |  | NOI TO COMPLETION OF FINAL ERA ACTION
|  |  |  | NOI Date | DEIS Date | NOI TO DEIS (DAYS) | NOI TO DEIS (MONTHS) | NOI TO DEIS (YEARS) | FEIS Date | DEIS TO FEIS NOA (DAYS) | DEIS TO FEIS NOA (MONTHS) | DEIS TO FEIS NOA (YEARS) | ROD Date | FEIS TO ROD (DAYS) | FEIS TO ROD (MONTHS) | FEIS TO ROD (YEARS) | NOI TO ROD (DAYS) | NOI TO ROD (MONTHS) | NOI TO ROD (YEARS) | Consultation Package Deemed Complete | Conclusion of EFH Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Consultation Package Deemed Complete- Formal1 | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Consultation Package Deemed Complete- Formal1 | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Consultation Initiated with SHPO/THPO | Section 106 Concluded | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Pre-Construction Notification/ Application Received | Final Verification/ Permit Decision Rendered | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Completed Permit Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Last Approval Date | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS)
Southline Transmission Project | BLM | The Southline Transmission Projects consists of two sections. The New Build Section would involve the construction of approximately 240 miles of new 345-kilovolt (kV) double-circuit electric transmission lines in New Mexico and Arizona, and would provide a capacity of up to 1,000 megawatts (MW). The Upgrade Section would consist of double-circuit 230-kV lines connecting the Apache Substation to the existing Saguaro Substation northwest of Tucson, Arizona. | $800 million | 2012-04-04 | 2014-04-11 | 737 | 24.5667 | 2.0192 | 2015-11-06 | 574 | 19.1333 | 1.5726 | 2016-04-21 | 167 | 5.5667 | 0.45753 | 1478 | 49.2667 | 4.0493 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-04-03 | 2015-11-10 | 586 | 19.5333 | 1.6055 | 2012-04-11 | 2016-03-14 | 1433 | 47.7667 | 3.926 | N/A | N/A | N/A | N/A | N/A | 2010-12-22 | 2016-04-21 | 1947 | 64.9 | 5.3342 | 2009-12-07 | Not Completed | N/A | N/A | N/A | 2016-04-21 | 1478 | 49.2667 | 4.0493
TransWest Express Transmission Project | BLM | The TransWest Express Transmission Project consists of a 725-mile 600kV DC line from Sinclair, WY substation to Marketplace, NV substation. The project is designed to carry renewable and other energy generated in Wyoming to the desert southwest. | $3 billion | 2011-01-04 | 2013-06-28 | 906 | 30.2 | 2.4822 | 2015-05-01 | 672 | 22.4 | 1.8411 | 2016-12-13 | 592 | 19.7333 | 1.6219 | 2170 | 72.3333 | 5.9452 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-08-25 | 2016-08-25 | 1 | 0.033333 | 0.0027397 | 2010-07-20 | 2016-10-18 | 2282 | 76.0667 | 6.2521 | N/A | N/A | N/A | N/A | N/A | 2015-11-10 | 2016-12-13 | 399 | 13.3 | 1.0932 | 2007-11-30 | 2017-05-31 | 3470 | 115.6667 | 9.5068 | 2016-12-13 | 2170 | 72.3333 | 5.9452
Energy Gateway South Transmission Project | BLM | The Applicant proposes to construct, operate, and maintain a 500-kilovolt (kV), overhead, single-circuit, alternating-current transmission line beginning near Medicine Bow, Carbon County, Wyoming, at the Aeolus Substation, planned as part of Gateway West, and would extend south and west to Clover Substation (constructed as part of Gateway Central) near Mona, Juab County, Utah, an approximate distance of 425 miles (230 miles on BLM lands). | $2.8 billion | 2011-04-01 | 2014-02-21 | 1057 | 35.2333 | 2.8959 | 2016-05-13 | 812 | 27.0667 | 2.2247 | 2016-12-13 | 214 | 7.1333 | 0.5863 | 2083 | 69.4333 | 5.7068 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-09-21 | 2016-01-15 | 116 | 3.8667 | 0.31781 | 2010-04-15 | 2016-12-09 | 2430 | 81 | 6.6575 | N/A | N/A | N/A | N/A | N/A | 2015-04-08 | 2016-12-13 | 615 | 20.5 | 1.6849 | 2008-12-13 | 2017-05-31 | 3091 | 103.0333 | 8.4685 | 2017-05-31 | 2252 | 75.0667 | 6.1699
Sigurd to Red Butte No. 2 345kV Transmission Project | BLM | The proposed project will consist of a new, single-circuit 345,000-volt transmission line connecting the Sigurd substation, located approximately six miles northeast of Richfield in Sevier County, Utah, to the Red Butte substation, located southwest of the town of Central in Washington County, Utah. | $358 million | 2010-01-05 | 2011-06-03 | 514 | 17.1333 | 1.4082 | 2012-10-05 | 490 | 16.3333 | 1.3425 | 2012-12-07 | 63 | 2.1 | 0.1726 | 1067 | 35.5667 | 2.9233 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-15 | 2012-11-09 | N/A | N/A | 55 | 1.8333 | 0.15068 | 2010-04-15 | 2012-11-29 | 959 | 31.9667 | 2.6274 | 2012-09-27 | 2012-12-12 | 76 | 2.5333 | 0.20822 | 2011-07-05 | 2012-12-07 | 521 | 17.3667 | 1.4274 | 2008-12-19 | 2012-12-07 | 1449 | 48.3 | 3.9699 | 2012-12-12 | 1072 | 35.7333 | 2.937
Southern California Edison's Eldorado-Ivanpah Transmission Line Project | BLM | The Southern California Edison's Eldorado-Ivanpah Transmission Line Project consists of constructing, operating, and maintaining new and upgraded transmission facilities between Clark County, NV, and San Bernadino County, CA. | $308+ million | 2009-07-27 | 2010-05-07 | 284 | 9.4667 | 0.77808 | 2010-12-17 | 224 | 7.4667 | 0.6137 | 2011-05-19 | 153 | 5.1 | 0.41918 | 661 | 22.0333 | 1.811 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-08-17 | 2011-04-29 | 255 | 8.5 | 0.69863 | 2009-01-01 | 2010-09-27 | 634 | 21.1333 | 1.737 | N/A | N/A | N/A | N/A | N/A | 2008-08-22 | 2011-05-19 | 1000 | 33.3333 | 2.7397 | N/A | N/A | N/A | N/A | N/A | 2011-05-19 | 661 | 22.0333 | 1.811
ON Line Project (Previously Known as Ely Energy Center) | BLM | This project consisted of the construction of 235 miles of 500kV transmission line from the newly constructed Robinson Summit Substation near Ely, Nevada, to the Harry Allen Substation north of North Las Vegas, Nevada. | $552 million | 2009-07-29 | 2009-11-06 | 100 | 3.3333 | 0.27397 | 2010-12-06 | 395 | 13.1667 | 1.0822 | 2011-03-18 | 102 | 3.4 | 0.27945 | 597 | 19.9 | 1.6356 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-10-13 | 2011-01-20 | 99 | 3.3 | 0.27123 | 2007-10-29 | 2010-05-18 | 932 | 31.0667 | 2.5534 | 2011-04-04 | 2011-05-03 | 29 | 0.96667 | 0.079452 | 2009-03-30 | 2011-03-18 | 718 | 23.9333 | 1.9671 | N/A | N/A | N/A | N/A | N/A | 2011-05-03 | 643 | 21.4333 | 1.7616
West Butte Wind Power Project | BLM | The project would include an 100-foot-wide, 3.9-mile-long ROW across federally administered lands for the construction and operation of an access road and transmission line. | $212.6 million | 2010-01-19 | 2010-04-02 | 73 | 2.4333 | 0.2 | 2010-10-01 | 182 | 6.0667 | 0.49863 | 2011-07-14 | 286 | 9.5333 | 0.78356 | 541 | 18.0333 | 1.4822 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-09-15 | 2011-04-11 | 573 | 19.1 | 1.5699 | N/A | N/A | N/A | N/A | N/A | 2008-12-15 | 2011-07-14 | 941 | 31.3667 | 2.5781 | N/A | N/A | N/A | N/A | N/A | 2011-07-14 | 541 | 18.0333 | 1.4822
Plains and Eastern Clean Line Transmission Line Project | DOE | The project would build additional facilities that would connect to the Project in Texas and Tennessee. The Project would deliver up to 4,000 megawatts (MW) of primarily wind generation from the Oklahoma and Texas Panhandle region to the mid-South and Southeastern United States, which could meet the annual energy needs of more than 1.5 million average American homes. | $3.5 billion | 2012-12-21 | 2014-12-19 | 728 | 24.2667 | 1.9945 | 2015-11-13 | 329 | 10.9667 | 0.90137 | 2016-03-31 | 139 | 4.6333 | 0.38082 | 1196 | 39.8667 | 3.2767 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-07-15 | 2015-11-20 | 128 | 4.2667 | 0.35068 | 2012-11-20 | 2015-12-07 | 1112 | 37.0667 | 3.0466 | 2016-11-07 | 2017-09-27 | 324 | 10.8 | 0.88767 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-09-27 | 1741 | 58.0333 | 4.7699
Antelope Valley Station to Neset Transmission Project | RUS | The Project includes construction and operation of approximately 190 miles of new 345-kV single pole transmission line, 2 new substations, modifications to 4 existing substations, a 345 kV switchyard, maintenance access roads, temporary construction roads, river crossings, temporary construction staging sites, and other facilities to be described in the proposed EIS. The proposed Project would be located in portions of Billings, Dunn, McKenzie, Mercer, Mountrail, and Williams Counties in western North Dakota. The Project would connect to the Integrated System at several locations, including Western's Williston Substation. | $507-$587 million | 2011-11-02 | 2012-12-07 | 401 | 13.3667 | 1.0986 | 2014-05-30 | 539 | 17.9667 | 1.4767 | 2014-09-22 | 115 | 3.8333 | 0.31507 | 1055 | 35.1667 | 2.8904 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-03-15 | 2014-11-21 | 251 | 8.3667 | 0.68767 | 2011-11-15 | 2014-07-02 | 960 | 32 | 2.6301 | 2014-12-01 | 2014-12-07 | 6 | 0.2 | 0.016438 | N/A | N/A | N/A | N/A | N/A | 2011-12-07 | 2014-09-05 | 1003 | 33.4333 | 2.7479 | 2014-12-07 | 1131 | 37.7 | 3.0986
Barren Ridge Renewable Transmission Project | USFS | The Barren Ridge Renewable Transmission Project (BRRTP) provides transmission access to approximately 1,000 megawatts of power from wind and solar projects in the Tehachapi Mountains and Mojave Desert areas. | $300 million | 2008-04-07 | 2011-08-26 | 1236 | 41.2 | 3.3863 | 2012-08-10 | 350 | 11.6667 | 0.9589 | 2012-09-24 | 45 | 1.5 | 0.12329 | 1631 | 54.3667 | 4.4685 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2008-04-15 | 2008-05-01 | 2012-04-05 | 2012-09-17 | 165 | 5.5 | 0.45205 | 2009-02-05 | 2012-06-23 | 1234 | 41.1333 | 3.3808 | 2015-06-21 | 2018-03-27 | 1010 | 33.6667 | 2.7671 | 2007-12-26 | 2015-01-10 | 2572 | 85.7333 | 7.0466 | 2007-02-12 | 2014-09-13 | 2770 | 92.3333 | 7.589 | 2018-03-27 | 3641 | 121.3667 | 9.9753
Kake to Petersburg Transmission Line Intertie Project | USFS | The project will construct an electric transmission line between Petersburg on Mitkof Island and the city of Kake on Kupreanof Island. The transmission line will be approximately 60 miles long and follow existing roads for 34 miles. | >$200 million | 2014-07-28 | 2014-12-29 | 154 | 5.1333 | 0.42192 | 2016-07-07 | 556 | 18.5333 | 1.5233 | 2016-11-30 | 146 | 4.8667 | 0.4 | 856 | 28.5333 | 2.3452 | N/A | N/A | N/A | N/A | N/A | 2015-10-22 | 2016-01-04 | N/A | N/A | 74 | 2.4667 | 0.20274 | 2014-09-15 | 2016-01-04 | N/A | N/A | 476 | 15.8667 | 1.3041 | 2014-07-28 | 2015-09-15 | 414 | 13.8 | 1.1342 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-02-10 | 2016-11-30 | 2485 | 82.8333 | 6.8082 | 2016-11-30 | 856 | 28.5333 | 2.3452
San Luis Transmission Project | WAPA | The proposed project was to construct, own, operate, and maintain a new 230-kilovolt transmission line about 62 miles in length between WAPA's Tracy Substation and WAPA's San Luis Substation and a new 70-kV transmission line about 5 miles in length between the San Luis and O'Neill Substations. | $323.5 million | 2013-11-22 | 2015-07-17 | 602 | 20.0667 | 1.6493 | 2016-03-25 | 252 | 8.4 | 0.69041 | 2016-05-09 | 45 | 1.5 | 0.12329 | 899 | 29.9667 | 2.463 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-02-28 | 2017-03-17 | 17 | 0.56667 | 0.046575 | 2014-11-03 | 2018-06-12 | 1317 | 43.9 | 3.6082 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2018-06-12 | 1663 | 55.4333 | 4.5562
Big Eddy-Knight Transmission Project | BPA | The Big Eddy-Knight Transmission Project consists of a 28-mile-long, 500-kilovolt (kV) transmission line that runs between BPA's existing Big Eddy Substation in The Dalles, Wasco County, Oregon, to a new Knight Substation about 4 miles northwest of Goldendale, Klickitat County, Washington. | $200 million | 2009-06-03 | 2010-12-10 | 555 | 18.5 | 1.5205 | 2011-07-15 | 217 | 7.2333 | 0.59452 | 2011-09-16 | 63 | 2.1 | 0.1726 | 835 | 27.8333 | 2.2877 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-06-03 | 2011-09-15 | 834 | 27.8 | 2.2849 | 2011-11-21 | 2014-07-22 | 974 | 32.4667 | 2.6685 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-07-22 | 1875 | 62.5 | 5.137
Appalachian National Scenic Trail Delaware Water Gap National Recreation Area Project | NPS | The project is to replace an existing 230kV transmission line with a double circuit transmission line carrying both a 230kV line capable of being energized to 500kV and a new 500kV line across the Delaware Water Gap National Recreation Area, Middle Delaware National Scenic and Recreational River, and Appalachian National Scenic Trail, in Pennsylvania and New Jersey. | $1.4-$2.3 billion | 2010-01-21 | 2011-11-25 | 673 | 22.4333 | 1.8438 | 2012-08-31 | 280 | 9.3333 | 0.76712 | 2012-10-01 | 31 | 1.0333 | 0.084932 | 984 | 32.8 | 2.6959 | 2010-05-13 | 2010-06-26 | 44 | 1.4667 | 0.12055 | N/A | N/A | 2010-05-13 | 2010-06-26 | 44 | 1.4667 | 0.12055 | N/A | N/A | 2010-05-13 | 2012-07-06 | 785 | 26.1667 | 2.1507 | 2010-02-01 | 2012-10-17 | 989 | 32.9667 | 2.7096 | 2012-04-05 | 2016-08-02 | 1580 | 52.6667 | 4.3288 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-08-02 | 2385 | 79.5 | 6.5342
Tehachapi Renewable Transmission Project New Information on Changed Conditions Caused by the Station Fire Construct Operate and Maintain New and Upgraded 500 kV and 220kV Transmission Lines and Substations Special Use Authorization Angeles National Forest Los Angeles County CA | USFS | Construct,operate, and maintain new and upgraded 500 kV and 220kV transmission lines and substations. | $1.8billion | 2007-09-07 | 2009-02-20 | 532 | 17.7333 | 1.4575 | 2010-09-24 | 581 | 19.3667 | 1.5918 | 2010-10-04 | 10 | 0.33333 | 0.027397 | 1123 | 37.4333 | 3.0767 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-12-15 | 2010-07-31 | 228 | 7.6 | 0.62466 | 2007-08-31 | 2010-02-11 | 895 | 29.8333 | 2.4521 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2007-06-29 | 2010-10-04 | 1193 | 39.7667 | 3.2685 | 2010-10-04 | 1123 | 37.4333 | 3.0767
Hampton - Rochester - La Crosse Transmission System Improvement Project | RUS | The project would construct a new 345 kV and a new 161kV transmission line from the Hampton Substation, through Rochester, to a proposed substation in La Crosse, WI. | $507 million | 2009-05-28 | 2011-12-16 | 932 | 31.0667 | 2.5534 | 2012-07-20 | 217 | 7.2333 | 0.59452 | 2013-01-11 | 175 | 5.8333 | 0.47945 | 1324 | 44.1333 | 3.6274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-08-05 | 2015-08-12 | 7 | 0.23333 | 0.019178 | 2012-07-27 | 2012-10-03 | 68 | 2.2667 | 0.1863 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-08-12 | 2267 | 75.5667 | 6.211
Gateway West Segments 8 & 9 | BLM | The primary component consists of two new 500-kV transmission lines on steel lattice towers. The BLM ROW grant area for the transmission line will be 250 feet wide for each 500-kV line, extending to 500 feet in width where the Segment 8 and 9 lines are adjacent. Access roads located in the transmission line ROW grant area are included in the authorized use. | >$200 million | 2014-09-19 | 2016-09-02 | 714 | 23.8 | 1.9562 | 2016-10-07 | 35 | 1.1667 | 0.09589 | 2017-01-19 | 104 | 3.4667 | 0.28493 | 853 | 28.4333 | 2.337 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-04-15 | 2013-09-12 | 150 | 5 | 0.41096 | 2009-04-09 | 2013-08-12 | 1586 | 52.8667 | 4.3452 | N/A | N/A | N/A | N/A | N/A | 2007-05-07 | 2017-01-19 | 3545 | 118.1667 | 9.7123 | N/A | N/A | N/A | N/A | N/A | 2017-01-19 | 853 | 28.4333 | 2.337
Mona to Oquirrh Transmission Corridor Project and Draft Pony Express Resource Management Plan Amendment | BLM | Construct, operate, and maintain a 69-mile long, single-circuit 500-kilovolt (kV) transmission line (which would be operated initially at 345kV) from the existing Mona Substation near the community of Mona in Juab County, Utah, to a proposed Mona Annex Substation (to be located south of the existing Mona Substation) that would be designed to accommodate 500, 345, and 138,V transmission lines, then on to a proposed future Limber Substation (to be located in the Tooele Valley in Utah), also designed to accommodate 500, 345, and 138kV transmission lines. Two double-circuit 345kV lines are proposed from the Limber Substation. One line would extend 31 miles to the existing Oquirrh Substation in West Jordan, Utah, and the second line would extend 45 miles to the existing Terminal Substation in Salt Lake City, Utah. | $383 million | 2007-10-16 | 2009-05-15 | 577 | 19.2333 | 1.5808 | 2010-04-26 | 346 | 11.5333 | 0.94795 | 2011-02-04 | 284 | 9.4667 | 0.77808 | 1207 | 40.2333 | 3.3068 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2007-07-06 | 2009-09-15 | N/A | N/A | 802 | 26.7333 | 2.1973 | 2007-11-15 | 2010-01-01 | 778 | 25.9333 | 2.1315 | N/A | N/A | N/A | N/A | N/A | 2007-01-30 | 2011-02-04 | 1466 | 48.8667 | 4.0164 | N/A | N/A | N/A | N/A | N/A | 2011-02-04 | 1207 | 40.2333 | 3.3068
SunZia Southwest Transmission Project Proposed Resource Management Plan Amendments | BLM | The SunZia Southwest Transmission Project (SunZia or the Project) is an extra high voltage 500kV interstate transmission infrastructure project that will enable the delivery of electric energy from hihg capacity wind energy regions in eastern New Mexico to customers in the Desert Southwest. The Project will consist of two 500 kV transmission lines and substations and will stretch over 500 miles. Originating in wind energy-rich eastern New Mexico at the SunZia East Substation, to the existing Pinal Central Substation near Coolidge, AZ. Construction of the first transmission line and substations is slated to begin in mid-2018, with commercial operation in late 2010. The project's total transfer capacity is 3,000MW. The Project is being developed jointly by Southwestern Power Group and Pattern Development and is estimated to cost over $1.5 billion. | $1.5 billion | 2009-05-29 | 2012-05-25 | 1092 | 36.4 | 2.9918 | 2013-06-14 | 385 | 12.8333 | 1.0548 | 2015-01-23 | 588 | 19.6 | 1.611 | 2065 | 68.8333 | 5.6575 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-07-02 | 2013-11-13 | 134 | 4.4667 | 0.36712 | 2009-05-15 | 2014-12-17 | 2042 | 68.0667 | 5.5945 | N/A | N/A | N/A | N/A | N/A | 2008-09-11 | 2015-01-23 | 2325 | 77.5 | 6.3699 | N/A | N/A | N/A | N/A | N/A | 2015-01-23 | 2065 | 68.8333 | 5.6575
*Projects in bold were covered by FAST-41. | [5 empty] | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS
[5 empty] | AVERAGE/ MEAN NOI TO DEIS: | 624.5789 | 20.8193 | 1.7112 | AVERAGE/ MEAN DEIS TO FEIS NOA: | 391.3684 | 13.0456 | 1.0722 | AVERAGE/ MEAN FEIS TO ROD: | 174.8421 | 5.8281 | 0.47902 | AVERAGE/ MEAN NOI TO ROD: | 39.693 | 3.2624 | AVERAGE/MEAN NMFS EFH REVIEW: |  | 44 | 1.4667 | 0.12055 |  |  | AVERAGE/MEAN NMFS ESA CONSULTATION: |  | 59 | 1.9667 | 0.16164 |  |  | AVERAGE/MEAN USFWS ESA CONSULTATION: |  | 250.2941 | 8.3431 | 0.68574 | AVERAGE/MEAN SECTION 106 CONSULTATION: |  | 1130.1053 | 37.6702 | 3.0962 | AVERAGE/MEAN SECTION 10/404 REVIEW: |  | 571.2857 | 19.0429 | 1.5652 | AVERAGE/MEAN BLM RIGHT-OF-WAY APPROVAL: |  | 1459 | 48.6333 | 3.9973 | AVERAGE/MEAN USFS SPECIAL USE PERMIT APPROVAL: |  | 2208.7143 | 73.6238 | 6.0513 | AVERAGE/ MEAN NOI TO FINAL DATE: | 1559.1579 | 51.9719 | 4.2717
[5 empty] | MEDIAN NOI TO DEIS: | 602 | 20.0667 | 1.6493 | MEDIAN DEIS TO FEIS NOA: | 350 | 11.6667 | 0.9589 | MEDIAN FEIS TO ROD: | 139 | 4.6333 | 0.38082 | MEDIAN NOI TO ROD: | 35.5667 | 2.9233 | MEDIAN NMFS EFH REVIEW: |  | 44 | 1.4667 | 0.12055 |  |  | MEDIAN NMFS ESA CONSULTATION: |  | 59 | 1.9667 | 0.16164 |  |  | MEDIAN USFWS ESA CONSULTATION: |  | 150 | 5 | 0.41096 | MEDIAN SECTION 106 CONSULTATION: |  | 960 | 32 | 2.6301 | MEDIAN SECTION 10/404 REVIEW: |  | 324 | 10.8 | 0.88767 | MEDIAN BLM RIGHT-OF-WAY APPROVAL: |  | 1000 | 33.3333 | 2.7397 | MEDIAN USFS SPECIAL USE PERMIT APPROVAL: |  | 2485 | 82.8333 | 6.8082 | MEDIAN NOI TO FINAL DATE: | 1478 | 49.2667 | 4.0493
[5 empty] | 25TH PERCENTILE | 401 | 13.3667 | 1.0986 | 25TH PERCENTILE | 224 | 7.4667 | 0.6137 | 25TH PERCENTILE | 63 | 2.1 | 0.1726 | 25TH PERCENTILE | 28.4333 | 2.337 | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | 77 | 2.5667 | 0.21096 | 25TH PERCENTILE |  | 778 | 25.9333 | 2.1315 | 25TH PERCENTILE |  | 29 | 0.96667 | 0.079452 | 25TH PERCENTILE |  | 615 | 20.5 | 1.6849 | 25TH PERCENTILE |  | 1193 | 39.7667 | 3.2685 | 25TH PERCENTILE | 856 | 28.5333 | 2.3452
[5 empty] | 75TH PERCENTILE | 906 | 30.2 | 2.4822 | 75TH PERCENTILE | 556 | 18.5333 | 1.5233 | 75TH PERCENTILE | 214 | 7.1333 | 0.5863 | 75TH PERCENTILE | 49.2667 | 4.0493 | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | 365.5 | 12.1833 | 1.0014 | 75TH PERCENTILE |  | 1433 | 47.7667 | 3.926 | 75TH PERCENTILE |  | 1010 | 33.6667 | 2.7671 | 75TH PERCENTILE |  | 2325 | 77.5 | 6.3699 | 75TH PERCENTILE |  | 3091 | 103.0333 | 8.4685 | 75TH PERCENTILE | 2170 | 72.3333 | 5.9452
Formulas:
NOI TO DEIS (DAYS) = DATEDIF([NEPA],[DEIS Date],"d")
DEIS TO FEIS NOA (DAYS) = DATEDIF([DEIS Date],[FEIS Date],"d")
FEIS TO ROD (DAYS) = DATEDIF([FEIS Date],[ROD Date],"d")
NOI TO ROD (DAYS) = DATEDIF([NEPA],[ROD Date],"d")
COMPLETION TIME (DAYS) = DATEDIF(AI3,[Conclusion of ESA Consultation],"d")
COMPLETION TIME (DAYS) = DATEDIF([SECTION 106],[Section 106 Concluded],"d")

## FAST-41 ONLY
PROJECT NAME* | LEAD AGENCY | PROJECT DESCRIPTION | PROJECT COST | NEPA | [15 empty] | NMFS EFH CONSULTATION |  |  |  |  | NMFS ESA CONSULTATION | [6 empty] | USFWS ESA CONSULTATION | [6 empty] | SECTION 106 |  |  |  |  | USACE SECTION 10/404 |  |  |  |  | BLM RIGHT-OF-WAY |  |  |  |  | USFS SPECIAL USE PERMIT |  |  |  |  | NOI TO COMPLETION OF FINAL ERA ACTION
|  |  |  | NOI Date | DEIS Date | NOI TO DEIS (DAYS) | NOI TO DEIS (MONTHS) | NOI TO DEIS (YEARS) | FEIS Date | DEIS TO FEIS NOA (DAYS) | DEIS TO FEIS NOA (MONTHS) | DEIS TO FEIS NOA (YEARS) | ROD Date | FEIS TO ROD (DAYS) | FEIS TO ROD (MONTHS) | FEIS TO ROD (YEARS) | NOI TO ROD (DAYS) | NOI TO ROD (MONTHS) | NOI TO ROD (YEARS) | Consultation Package Deemed Complete | Conclusion of EFH Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Consultation Package Deemed Complete- Formal1 | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Consultation Package Deemed Complete- Formal1 | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Consultation Initiated with SHPO/THPO | Section 106 Concluded | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Pre-Construction Notification/ Application Received | Final Verification/ Permit Decision Rendered | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Completed Permit Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Last Approval Date | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS)
TransWest Express Transmission Project | BLM | The TransWest Express Transmission Project consists of a 725-mile 600kV DC line from Sinclair, WY substation to Marketplace, NV substation. The project is designed to carry renewable and other energy generated in Wyoming to the desert southwest. | $3 billion | 2011-01-04 | 2013-06-28 | 906 | 30.2 | 2.4822 | 2015-05-01 | 672 | 22.4 | 1.8411 | 2016-12-13 | 592 | 19.7333 | 1.6219 | 2170 | 72.3333 | 5.9452 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-08-25 | 2016-08-25 | 1 | 0.033333 | 0.0027397 | 2010-07-20 | 2016-10-18 | 2282 | 76.0667 | 6.2521 | N/A | N/A | N/A | N/A | N/A | 2015-11-10 | 2016-12-13 | 399 | 13.3 | 1.0932 | 2007-11-30 | 2017-05-31 | 3470 | 115.6667 | 9.5068 | 2016-12-13 | 2170 | 72.3333 | 5.9452
Energy Gateway South Transmission Project | BLM | The Applicant proposes to construct, operate, and maintain a 500-kilovolt (kV), overhead, single-circuit, alternating-current transmission line beginning near Medicine Bow, Carbon County, Wyoming, at the Aeolus Substation, planned as part of Gateway West, and would extend south and west to Clover Substation (constructed as part of Gateway Central) near Mona, Juab County, Utah, an approximate distance of 425 miles (230 miles on BLM lands). | $2.8 billion | 2011-04-01 | 2014-02-21 | 1057 | 35.2333 | 2.8959 | 2016-05-13 | 812 | 27.0667 | 2.2247 | 2016-12-13 | 214 | 7.1333 | 0.5863 | 2083 | 69.4333 | 5.7068 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-09-21 | 2016-01-15 | 116 | 3.8667 | 0.31781 | 2010-04-15 | 2016-12-09 | 2430 | 81 | 6.6575 | N/A | N/A | N/A | N/A | N/A | 2015-04-08 | 2016-12-13 | 615 | 20.5 | 1.6849 | 2008-12-13 | 2017-05-31 | 3091 | 103.0333 | 8.4685 | 2017-05-31 | 2252 | 75.0667 | 6.1699
Plains and Eastern Clean Line Transmission Line Project | DOE | The project would build additional facilities that would connect to the Project in Texas and Tennessee. The Project would deliver up to 4,000 megawatts (MW) of primarily wind generation from the Oklahoma and Texas Panhandle region to the mid-South and Southeastern United States, which could meet the annual energy needs of more than 1.5 million average American homes. | $3.5 billion | 2012-12-21 | 2014-12-19 | 728 | 24.2667 | 1.9945 | 2015-11-13 | 329 | 10.9667 | 0.90137 | 2016-03-31 | 139 | 4.6333 | 0.38082 | 1196 | 39.8667 | 3.2767 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-07-15 | 2015-11-20 | 128 | 4.2667 | 0.35068 | 2012-11-20 | 2015-12-07 | 1112 | 37.0667 | 3.0466 | 2016-11-07 | 2017-09-27 | 324 | 10.8 | 0.88767 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-09-27 | 1741 | 58.0333 | 4.7699
Kake to Petersburg Transmission Line Intertie Project | USFS | The project will construct an electric transmission line between Petersburg on Mitkof Island and the city of Kake on Kupreanof Island. The transmission line will be approximately 60 miles long and follow existing roads for 34 miles. | >$200 million | 2014-07-28 | 2014-12-29 | 154 | 5.1333 | 0.42192 | 2016-07-07 | 556 | 18.5333 | 1.5233 | 2016-11-30 | 146 | 4.8667 | 0.4 | 856 | 28.5333 | 2.3452 | N/A | N/A | N/A | N/A | N/A | 2015-10-22 | 2016-01-04 | N/A | N/A | 74 | 2.4667 | 0.20274 | 2014-09-15 | 2016-01-04 | N/A | N/A | 476 | 15.8667 | 1.3041 | 2014-07-28 | 2015-09-15 | 414 | 13.8 | 1.1342 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-02-10 | 2016-11-30 | 2485 | 82.8333 | 6.8082 | 2016-11-30 | 856 | 28.5333 | 2.3452
Gateway West Segments 8 & 9 | BLM | The primary component consists of two new 500-kV transmission lines on steel lattice towers. The BLM ROW grant area for the transmission line will be 250 feet wide for each 500-kV line, extending to 500 feet in width where the Segment 8 and 9 lines are adjacent. Access roads located in the transmission line ROW grant area are included in the authorized use. | >$200 million | 2014-09-19 | 2016-09-02 | 714 | 23.8 | 1.9562 | 2016-10-07 | 35 | 1.1667 | 0.09589 | 2017-01-19 | 104 | 3.4667 | 0.28493 | 853 | 28.4333 | 2.337 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-04-15 | 2013-09-12 | 150 | 5 | 0.41096 | 2009-04-09 | 2013-08-12 | 1586 | 52.8667 | 4.3452 | N/A | N/A | N/A | N/A | N/A | 2007-05-07 | 2017-01-19 | 3545 | 118.1667 | 9.7123 | N/A | N/A | N/A | N/A | N/A | 2017-01-19 | 853 | 28.4333 | 2.337
*Projects in bold were covered by FAST-41. | [5 empty] | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS
[5 empty] | AVERAGE/ MEAN NOI TO DEIS: | 711.8 | 23.7267 | 1.9501 | AVERAGE/ MEAN DEIS TO FEIS NOA: | 480.8 | 16.0267 | 1.3173 | AVERAGE/ MEAN FEIS TO ROD: | 239 | 7.9667 | 0.65479 | AVERAGE/ MEAN NOI TO ROD: | 47.72 | 3.9222 | AVERAGE/MEAN NMFS EFH REVIEW: |  | #DIV/0! | 0 | 0 |  |  | AVERAGE/MEAN NMFS ESA CONSULTATION: |  | 74 | 2.4667 | 0.20274 |  |  | AVERAGE/MEAN USFWS ESA CONSULTATION: |  | 174.2 | 5.8067 | 0.47726 | AVERAGE/MEAN SECTION 106 CONSULTATION: |  | 1564.8 | 52.16 | 4.2871 | AVERAGE/MEAN SECTION 10/404 REVIEW: |  | 324 | 10.8 | 0.88767 | AVERAGE/MEAN BLM RIGHT-OF-WAY APPROVAL: |  | 1519.6667 | 50.6556 | 4.1635 | AVERAGE/MEAN USFS SPECIAL USE PERMIT APPROVAL: |  | 3015.3333 | 100.5111 | 8.2612 | AVERAGE/ MEAN NOI TO FINAL DATE: | 1574.4 | 52.48 | 4.3134
[5 empty] | MEDIAN NOI TO DEIS: | 728 | 24.2667 | 1.9945 | MEDIAN DEIS TO FEIS NOA: | 556 | 18.5333 | 1.5233 | MEDIAN FEIS TO ROD: | 146 | 4.8667 | 0.4 | MEDIAN NOI TO ROD: | 39.8667 | 3.2767 | MEDIAN NMFS EFH REVIEW: |  | #NUM! | 0 | 0 |  |  | MEDIAN NMFS ESA CONSULTATION: |  | 74 | 2.4667 | 0.20274 |  |  | MEDIAN USFWS ESA CONSULTATION: |  | 128 | 4.2667 | 0.35068 | MEDIAN SECTION 106 CONSULTATION: |  | 1586 | 52.8667 | 4.3452 | MEDIAN SECTION 10/404 REVIEW: |  | 324 | 10.8 | 0.88767 | MEDIAN BLM RIGHT-OF-WAY APPROVAL: |  | 615 | 20.5 | 1.6849 | MEDIAN USFS SPECIAL USE PERMIT APPROVAL: |  | 3091 | 103.0333 | 8.4685 | MEDIAN NOI TO FINAL DATE: | 1741 | 58.0333 | 4.7699
[5 empty] | 25TH PERCENTILE | 434 | 14.4667 | 1.189 | 25TH PERCENTILE | 182 | 6.0667 | 0.49863 | 25TH PERCENTILE | 121.5 | 4.05 | 0.33288 | 25TH PERCENTILE | 28.4833 | 2.3411 | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | 58.5 | 1.95 | 0.16027 | 25TH PERCENTILE |  | 763 | 25.4333 | 2.0904 | 25TH PERCENTILE |  | #NUM! | #NUM! | #NUM! | 25TH PERCENTILE |  | 399 | 13.3 | 1.0932 | 25TH PERCENTILE |  | 2485 | 82.8333 | 6.8082 | 25TH PERCENTILE | 854.5 | 28.4833 | 2.3411
[5 empty] | 75TH PERCENTILE | 981.5 | 32.7167 | 2.689 | 75TH PERCENTILE | 742 | 24.7333 | 2.0329 | 75TH PERCENTILE | 403 | 13.4333 | 1.1041 | 75TH PERCENTILE | 70.8833 | 5.826 | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | 313 | 10.4333 | 0.85753 | 75TH PERCENTILE |  | 2356 | 78.5333 | 6.4548 | 75TH PERCENTILE |  | #NUM! | #NUM! | #NUM! | 75TH PERCENTILE |  | 3545 | 118.1667 | 9.7123 | 75TH PERCENTILE |  | 3470 | 115.6667 | 9.5068 | 75TH PERCENTILE | 2211 | 73.7 | 6.0575
Formulas:
NOI TO DEIS (DAYS) = DATEDIF([NEPA],[DEIS Date],"d")
DEIS TO FEIS NOA (DAYS) = DATEDIF([DEIS Date],[FEIS Date],"d")
FEIS TO ROD (DAYS) = DATEDIF([FEIS Date],[ROD Date],"d")
NOI TO ROD (DAYS) = DATEDIF([NEPA],[ROD Date],"d")
COMPLETION TIME (DAYS) = DATEDIF([SECTION 106],[Section 106 Concluded],"d")
COMPLETION TIME (DAYS) = DATEDIF([BLM RIGHT-OF-WAY],[Permit Approved],"d")