## ALL
PROJECT NAME* | LEAD AGENCY | PROJECT DESCRIPTION | PROJECT COST | NEPA | [15 empty] | NMFS EFH CONSULTATION |  |  |  |  | NMFS ESA CONSULTATION | [6 empty] | FWS ESA CONSULTATION | [6 empty] | SECTION 106 |  |  |  |  | USACE SECTION 10/404 |  |  |  |  | BLM RIGHT-OF-WAY |  |  |  |  | FS SPECIAL USE PERMIT |  |  |  |  | NOI TO COMPLETION OF FINAL ERA ACTION
|  |  |  | NOI Date | DEIS Date | NOI TO DEIS (DAYS) | NOI TO DEIS (MONTHS) | NOI TO DEIS (YEARS) | FEIS Date | DEIS TO FEIS NOA (DAYS) | DEIS TO FEIS NOA (MONTHS) | DEIS TO FEIS NOA (YEARS) | ROD Date | FEIS TO ROD (DAYS) | FEIS TO ROD (MONTHS) | FEIS TO ROD (YEARS) | NOI TO ROD (DAYS) | NOI TO ROD (MONTHS) | NOI TO ROD (YEARS) | Consultation Package Deemed Complete | Conclusion of EFH Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Formal Consultation Initiated | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Formal Consultation Initiated | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Consultation Initated with SHPO/THPO | Section 106 Concluded | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Pre-Construction Notification (PCN)/ Application Received | Final Verification/ Permit Decision Rendered | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Completed Permit Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Last Approval Date | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS)
Moapa Southern Paiute Solar Project | BIA | The Moapa Southern Paiute Solar project involves the construction of a 250 megawatt (MW) solar generation facility and associated infrastructure on the Reservation. The project also includes the development of a 12 kV transmission line and water line along with obtaining a grant of easement on BLM lands for an up to 500 kV transmission line and access roads. | $500 million - $1.6 billion | 2011-02-04 | 2011-11-25 | 294 | 9.8 | 0.80548 | 2012-03-16 | 112 | 3.7333 | 0.30685 | 2012-06-21 | 97 | 3.2333 | 0.26575 | 503 | 16.7667 | 1.3781 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-20 | 2012-03-07 | 169 | 5.6333 | 0.46301 | 2011-02-04 | 2011-11-08 | 277 | 9.2333 | 0.7589 | 2011-07-29 | 2011-08-20 | 22 | 0.73333 | 0.060274 | 2010-09-15 | 2012-06-21 | 645 | 21.5 | 1.7671 | N/A | N/A | N/A | N/A | N/A | 2012-06-21 | 503 | 16.7667 | 1.3781
McCoy Solar Energy Project | BLM | The project will construct, operate, maintain, and decommission an up to 750 megawatt (MW) photovoltaic solar energy generation facility and necessary ancillary facilities including a generation tie (gen-tie) line, access road and switch yard. Entails a footprint of approximately 4,893 acres for the solar facility, a 14.5-mile generation tie line, with a ROW width of 100 feet, access roads, a distribution line, and a 2-acre switch yard (total linear disturbance is 146 acres. | $1.2 billion | 2011-08-29 | 2012-05-25 | 270 | 9 | 0.73973 | 2012-12-21 | 210 | 7 | 0.57534 | 2013-03-13 | 82 | 2.7333 | 0.22466 | 562 | 18.7333 | 1.5397 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-03-16 | 2013-03-06 | 355 | 11.8333 | 0.9726 | 2011-08-17 | 2013-02-22 | 555 | 18.5 | 1.5205 | N/A | N/A | N/A | N/A | N/A | 2011-08-29 | 2013-03-13 | 562 | 18.7333 | 1.5397 | N/A | N/A | N/A | N/A | N/A | 2013-03-13 | 562 | 18.7333 | 1.5397
Crescent Dunes Solar Energy Project | BLM | The project will construct and operate a 110-megawatt (MW) solar power generating facility based on concentrating solar power technology, an approximately 9.5-mile 230 kilovolt (kV) TL, and the temporary use of a 40-acre borrow pit to extract aggregate for construction. | $737+ million | 2009-11-24 | 2010-09-03 | 283 | 9.4333 | 0.77534 | 2010-11-19 | 77 | 2.5667 | 0.21096 | 2010-12-20 | 31 | 1.0333 | 0.084932 | 391 | 13.0333 | 1.0712 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-12-30 | 2010-05-17 | 138 | 4.6 | 0.37808 | N/A | N/A | N/A | N/A | N/A | 2009-11-24 | 2010-12-20 | 391 | 13.0333 | 1.0712 | N/A | N/A | N/A | N/A | N/A | 2010-12-20 | 391 | 13.0333 | 1.0712
Ivanpah Solar Electric Generating System Project | BLM | The project will construct a 400-megawatt concentrated solar power tower thermal-electric power plant and would be located on approximately 4,073 acres of public land approximately 5 miles southwest of Primm, NV in San Bernardino County, California. | $2.2 billion | 2008-11-06 | 2009-11-13 | 372 | 12.4 | 1.0192 | 2010-08-06 | 266 | 8.8667 | 0.72877 | 2010-10-07 | 62 | 2.0667 | 0.16986 | 700 | 23.3333 | 1.9178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-12-07 | 2010-10-01 | 298 | 9.9333 | 0.81644 | 2010-01-01 | 2010-09-15 | 257 | 8.5667 | 0.70411 | N/A | N/A | N/A | N/A | N/A | 2006-12-14 | 2010-10-07 | 1393 | 46.4333 | 3.8164 | N/A | N/A | N/A | N/A | N/A | 2010-10-07 | 700 | 23.3333 | 1.9178
First Solar Desert Sunlight Solar Farm Project | BLM | The project proposes to develop a 550-megawatt photovoltaic solar project and proposes to facilitate the construction and operation of the Red Bluff Substation, California Desert Conservation Area Plan, Riverside County, California. | $1.46 billion | 2010-01-13 | 2010-08-27 | 226 | 7.5333 | 0.61918 | 2011-04-05 | 221 | 7.3667 | 0.60548 | 2011-08-09 | 126 | 4.2 | 0.34521 | 573 | 19.1 | 1.5699 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-10-15 | 2011-07-06 | 264 | 8.8 | 0.72329 | 2010-11-01 | 2011-06-16 | 227 | 7.5667 | 0.62192 | 2010-09-01 | 2010-12-28 | 118 | 3.9333 | 0.32329 | 2010-08-15 | 2011-08-09 | 359 | 11.9667 | 0.98356 | N/A | N/A | N/A | N/A | N/A | 2011-08-09 | 573 | 19.1 | 1.5699
Ocotillo Express Wind Energy Project | BLM | The project consists of designing, constructing and operating a 265.4-megawatt (MW) wind farm, using 112 wind turbines, each with a nominal capacity of 2.37 MW. | $1 billion | 2010-12-13 | 2011-07-08 | 207 | 6.9 | 0.56712 | 2012-03-09 | 245 | 8.1667 | 0.67123 | 2012-05-11 | 63 | 2.1 | 0.1726 | 515 | 17.1667 | 1.411 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-08-08 | 2012-04-26 | 262 | 8.7333 | 0.71781 | 2011-03-22 | 2012-05-08 | 413 | 13.7667 | 1.1315 | 2012-04-03 | 2012-06-18 | 76 | 2.5333 | 0.20822 | 2010-12-13 | 2012-05-11 | 515 | 17.1667 | 1.411 | N/A | N/A | N/A | N/A | N/A | 2012-06-18 | 553 | 18.4333 | 1.5151
Imperial Valley Solar Project (Formerly Known as Stirling Energy Systems Solar 2 Project) | BLM | The project as licensed is a 709 megawatt concentrated solar power facility located 100 miles east of San Diego, 14 miles west of El Centro, and 4 miles east of Ocotillo Wells | $2 billion | 2008-10-10 | 2010-02-26 | 504 | 16.8 | 1.3808 | 2010-07-28 | 152 | 5.0667 | 0.41644 | 2010-10-05 | 69 | 2.3 | 0.18904 | 725 | 24.1667 | 1.9863 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-12-24 | 2010-09-23 | 273 | 9.1 | 0.74795 | 2009-08-25 | 2010-09-15 | 386 | 12.8667 | 1.0575 | 2012-08-15 | 2012-09-27 | 43 | 1.4333 | 0.11781 | 2009-02-15 | 2010-10-05 | 597 | 19.9 | 1.6356 | N/A | N/A | N/A | N/A | N/A | 2010-10-05 | 725 | 24.1667 | 1.9863
Amargosa Farm Road Solar Energy Project | BLM | The project will construct two concentrated solar thermal parabolic trough power plant facilities on public lands, approximately 80 miles northwest of Las Vegas, in Nye County, Nevada. | $2.5 - 3 billion | 2009-07-13 | 2010-03-19 | 249 | 8.3 | 0.68219 | 2010-10-15 | 210 | 7 | 0.57534 | 2010-11-15 | 31 | 1.0333 | 0.084932 | 490 | 16.3333 | 1.3425 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-09-10 | 2010-11-01 | 52 | 1.7333 | 0.14247 | 2009-10-01 | 2010-06-01 | 243 | 8.1 | 0.66575 | N/A | N/A | N/A | N/A | N/A | 2007-11-20 | 2010-11-15 | 1091 | 36.3667 | 2.989 | N/A | N/A | N/A | N/A | N/A | 2010-11-15 | 490 | 16.3333 | 1.3425
Mohave County Wind Farm Project | BLM | The project will construct, operate, maintain and decommission a wind energy facility and associated infrastructure in the White Hills area of northwestern Mohave County, Arizona. BP Wind Energy applied to Western Area Power Administration to interconnect the proposed project to one of two transmission lines crossing the Project Area. The proposed 500 MWwind farm site would occupy 38,099 acres of public land managed by the BLM, Kingman Field Office, and 8,960 acres of Federal land managed by the BOR. | $1 billion | 2010-07-26 | 2012-04-27 | 641 | 21.3667 | 1.7562 | 2013-05-17 | 385 | 12.8333 | 1.0548 | 2013-06-26 | 40 | 1.3333 | 0.10959 | 1066 | 35.5333 | 2.9205 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-03-29 | 2012-12-19 | 996 | 33.2 | 2.7288 | N/A | N/A | N/A | N/A | N/A | 2009-11-20 | 2013-06-26 | 1314 | 43.8 | 3.6 | N/A | N/A | N/A | N/A | N/A | 2013-06-23 | 1063 | 35.4333 | 2.9123
Chokecherry and Sierra Madre Wind Energy Project | BLM | The project will develop a 1,000-turbine wind farm that will be able to generate up to 3,000 megawatts of electrictity and is located south of Sinclair and Rawlins in Carbon County, Wyoming | $5 billion | 2008-07-09 | 2011-07-22 | 1108 | 36.9333 | 3.0356 | 2012-06-29 | 343 | 11.4333 | 0.93973 | 2012-10-09 | 102 | 3.4 | 0.27945 | 1553 | 51.7667 | 4.2548 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-08-27 | 2012-09-05 | 9 | 0.3 | 0.024658 | 2008-07-25 | 2012-08-23 | 1490 | 49.6667 | 4.0822 | N/A | N/A | N/A | N/A | N/A | 2008-01-30 | 2012-10-09 | 1714 | 57.1333 | 4.6959 | N/A | N/A | N/A | N/A | N/A | 2012-10-09 | 1553 | 51.7667 | 4.2548
Panoche Valley Solar Project | USACE | The project will create a 100-megawatt solar farm on nearly 3,200 acres in Panoche Valley, San Benito County. | $650 million | 2012-07-19 | 2015-09-11 | 1149 | 38.3 | 3.1479 | 2015-12-31 | 111 | 3.7 | 0.30411 | 2016-03-09 | 69 | 2.3 | 0.18904 | 1329 | 44.3 | 3.6411 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-11-17 | 2015-10-05 | 322 | 10.7333 | 0.88219 | 2015-09-16 | 2015-10-12 | 26 | 0.86667 | 0.071233 | 2010-08-15 | 2016-03-09 | 2033 | 67.7667 | 5.5699 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-03-09 | 1329 | 44.3 | 3.6411
Quartzsite Solar Energy Project and Proposed Yuma Field Office Resource Management Plan Amendment | WAPA | The project proposes to construct a 100-MW (net), solar-powered electrical generation facility in La Paz County, Ariz. | $700 - 800 million | 2010-01-14 | 2011-11-10 | 665 | 22.1667 | 1.8219 | 2012-12-21 | 407 | 13.5667 | 1.1151 | 2013-05-30 | 160 | 5.3333 | 0.43836 | 1232 | 41.0667 | 3.3753 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-09-15 | 2010-12-15 | 456 | 15.2 | 1.2493 | N/A | N/A | N/A | N/A | N/A | 2008-05-27 | 2013-05-30 | 1829 | 60.9667 | 5.011 | N/A | N/A | N/A | N/A | N/A | 2013-05-30 | 1232 | 41.0667 | 3.3753
Rice Solar Energy Project; Proposed 150 megawatt Solar Energy Generating Facility | WAPA | The project proposes to construct a 150-MW solar-powered electrical generation facility in eastern Riverside County, Calif. | $750 million | 2010-03-29 | 2010-10-22 | 207 | 6.9 | 0.56712 | 2011-06-10 | 231 | 7.7 | 0.63288 | 2011-12-08 | 181 | 6.0333 | 0.49589 | 619 | 20.6333 | 1.6959 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-01-18 | 2011-01-27 | 9 | 0.3 | 0.024658 | 2010-03-01 | 2011-02-01 | 337 | 11.2333 | 0.92329 | N/A | N/A | N/A | N/A | N/A | 2009-05-12 | 2011-12-08 | 940 | 31.3333 | 2.5753 | N/A | N/A | N/A | N/A | N/A | 2011-12-08 | 619 | 20.6333 | 1.6959
Grapevine Canyon Wind Project | WAPA | The project proposes to construct a wind energy generation project up to 500 megawatts. The project would be located on privately owned ranch lands and trust lands administered by the Arizona State Land Department. The project location is approximately 22 miles southeast of Flagstaff and about 18 miles south of the I-40 Twin Arrows interchange. | $240 million | 2009-07-24 | 2010-07-23 | 364 | 12.1333 | 0.99726 | 2012-06-08 | 686 | 22.8667 | 1.8795 | 2012-09-11 | 95 | 3.1667 | 0.26027 | 1145 | 38.1667 | 3.137 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-02-08 | 2012-03-15 | N/A | N/A | 36 | 1.2 | 0.09863 | 2009-10-15 | 2010-09-03 | 323 | 10.7667 | 0.88493 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-11 | 1145 | 38.1667 | 3.137
Eagle Mountain Pumped Storage Hydroelectric Project | FERC | The proposed project will create 1,300-megawatt of energy and would occupy nearly 675.63 acres of federal land managed by BLM and an additional 1,545.63 acres of private lands. | $2.5 billion | 2008-12-17 | 2010-12-30 | 743 | 24.7667 | 2.0356 | 2012-02-10 | 407 | 13.5667 | 1.1151 | 2014-06-19 | 860 | 28.6667 | 2.3562 | 2010 | 67 | 5.5068 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-04-21 | N/A | 2011-07-20 | 2012-04-10 | 265 | 8.8333 | 0.72603 | 2007-09-15 | 2011-09-27 | 1473 | 49.1 | 4.0356 | N/A | N/A | N/A | N/A | N/A | 2009-03-15 | 2018-08-01 | 3426 | 114.2 | 9.3863 | N/A | N/A | N/A | N/A | N/A | 2018-08-01 | 3514 | 117.1333 | 9.6274
Calico Solar Project Proposed Solar Thermal Electricity Generation Facility Project | BLM | Construction and operation of a 850 MW solar field on 8,230 acres in the Mojave Desert, and an associated 2-mile, 230 kV interconnection transmission line. | $2.6 billion | 2008-10-17 | 2010-04-02 | 532 | 17.7333 | 1.4575 | 2010-08-06 | 126 | 4.2 | 0.34521 | 2010-10-20 | 75 | 2.5 | 0.20548 | 733 | 24.4333 | 2.0082 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-07-19 | N/A | N/A | N/A | N/A | 2009-12-01 | 2010-09-22 | 295 | 9.8333 | 0.80822 | N/A | N/A | N/A | N/A | N/A | 2008-06-30 | 2010-10-20 | 842 | 28.0667 | 2.3068 | N/A | N/A | N/A | N/A | N/A | 2010-10-20 | 733 | 24.4333 | 2.0082
Blythe Solar Power Project | BLM | Blythe Solar Power Project (09-AFC-6). Application for Right-of Way Grant to Construct and Operate and Decommission a Solar Thermal Facility on Public Lands. Riverside County, CA | $1.13 billion | 2009-11-23 | 2010-03-19 | 116 | 3.8667 | 0.31781 | 2010-08-20 | 154 | 5.1333 | 0.42192 | 2010-10-22 | 63 | 2.1 | 0.1726 | 333 | 11.1 | 0.91233 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-07-27 | 2010-10-08 | 73 | 2.4333 | 0.2 | 2013-06-26 | 2013-11-18 | 145 | 4.8333 | 0.39726 | N/A | N/A | N/A | N/A | N/A | 2009-08-24 | 2010-10-22 | 424 | 14.1333 | 1.1616 | N/A | N/A | N/A | N/A | N/A | 2013-11-18 | 1456 | 48.5333 | 3.989
Sonoran Solar Energy Project | BLM | The project involved the construction and the operation of the Sonoran Solar Energy Project, a concentrated solar thermal power plant with ancillary linear facilities on approximately 3,620 acres. | $1.2+ billion | 2009-07-08 | 2010-04-09 | 275 | 9.1667 | 0.75342 | 2011-10-21 | 560 | 18.6667 | 1.5342 | 2011-12-19 | 59 | 1.9667 | 0.16164 | 894 | 29.8 | 2.4493 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2009-07-08 | 2009-08-11 | 2009-12-08 | 2010-01-11 | 34 | 1.1333 | 0.093151 | 2009-07-07 | 2011-11-23 | 700 | 23.3333 | 1.9178 | N/A | N/A | N/A | N/A | N/A | 2007-06-28 | 2011-12-19 | 1635 | 54.5 | 4.4795 | N/A | N/A | N/A | N/A | N/A | 2011-12-19 | 894 | 29.8 | 2.4493
Genesis Solar Energy Project | BLM | Genesis Solar, LLC, (Applicant) proposes to construct, operate, maintain and decommission the GSEP or Proposed Action which includes a 250 MW solar generating facility, 230-kV transmission line (gen-tie) and ancillary facilities (access road and natural gas pipeline) on BLM-administered land, approximately 25 miles west of the city of Blythe and five miles north of the Interstate-10 freeway . | $852+ million | 2009-11-23 | 2010-04-09 | 137 | 4.5667 | 0.37534 | 2010-08-27 | 140 | 4.6667 | 0.38356 | 2010-11-04 | 69 | 2.3 | 0.18904 | 346 | 11.5333 | 0.94795 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2010-07-13 | 2010-11-02 | 112 | 3.7333 | 0.30685 | 2010-02-25 | 2010-10-07 | 224 | 7.4667 | 0.6137 | N/A | N/A | N/A | N/A | N/A | 2007-01-31 | 2010-11-04 | 1373 | 45.7667 | 3.7616 | N/A | N/A | N/A | N/A | N/A | 2010-11-04 | 346 | 11.5333 | 0.94795
Boundary Hydroelectric Project | FERC | The project jointly filed an offer of settlement, consisting of two comprehensive settlement agreements, a joint explanatory statement and a request to consolidate the processing of Seattle's relicensing of the Boundary Project with the District's surrender of its license for the Sullivan Creek Project. | $852.9 million | 2010-09-22 | 2011-04-15 | 205 | 6.8333 | 0.56164 | 2011-09-16 | 154 | 5.1333 | 0.42192 | 2013-03-20 | 551 | 18.3667 | 1.5096 | 910 | 30.3333 | 2.4932 | N/A | N/A | N/A | N/A | N/A | 2005-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2004-08-20 | N/A | 2011-09-29 | 2012-06-19 | 264 | 8.8 | 0.72329 | 2005-03-09 | 2011-12-06 | 2463 | 82.1 | 6.7479 | 2014-06-02 | 2014-06-30 | 28 | 0.93333 | 0.076712 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-06-30 | 1377 | 45.9 | 3.7726
*Projects in bold were covered by FAST-41. | [5 empty] | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS
[5 empty] | AVERAGE/ MEAN NOI TO DEIS: | 427.35 | 14.245 | 1.1708 | AVERAGE/ MEAN DEIS TO FEIS NOA: | 259.85 | 8.6617 | 0.71192 | AVERAGE/ MEAN FEIS TO ROD: | 144.25 | 4.8083 | 0.39521 | AVERAGE/ MEAN NOI TO ROD: | 27.5772 | 2.2779 | AVERAGE/MEAN NMFS EFH CONSULTATION: |  | 0 | N/A | N/A |  |  | AVERAGE/MEAN NMFS ESA CONSULTATION: |  | 0 | N/A | N/A |  |  | AVERAGE/MEAN USFWS ESA CONSULTATION: |  | 174.8125 | 5.8271 | 0.47894 | AVERAGE/MEAN SECTION 106 CONSULTATION: |  | 571.2 | 19.04 | 1.5649 | AVERAGE/MEAN SECTION 10/404 REVIEW: |  | 386.6667 | 12.8889 | 1.0594 | AVERAGE/MEAN BLM RIGHT-OF-WAY APPROVAL: |  | 1120.5882 | 37.3529 | 3.0701 | AVERAGE/MEAN USFS SPECIAL USE PERMIT APPROVAL: |  | 0 | N/A | N/A | AVERAGE/ MEAN NOI TO FINAL DATE: | 967.4211 | 32.2474 | 2.6873
[5 empty] | MEDIAN NOI TO DEIS: | 288.5 | 9.6167 | 0.79041 | MEDIAN DEIS TO FEIS NOA: | 215.5 | 7.1833 | 0.59041 | MEDIAN FEIS TO ROD: | 72 | 2.4 | 0.19726 | MEDIAN NOI TO ROD: | 23.75 | 1.9521 | MEDIAN NMFS EFH CONSULTATION: |  | 0 | N/A | N/A |  |  | MEDIAN NMFS ESA CONSULTATION: |  | 0 | N/A | N/A |  |  | MEDIAN USFWS ESA CONSULTATION: |  | 215.5 | 7.1833 | 0.59041 | MEDIAN SECTION 106 CONSULTATION: |  | 330 | 11 | 0.90411 | MEDIAN SECTION 10/404 REVIEW: |  | 59.5 | 1.9833 | 0.16301 | MEDIAN BLM RIGHT-OF-WAY APPROVAL: |  | 940 | 31.3333 | 2.5753 | MEDIAN USFS SPECIAL USE PERMIT APPROVAL: |  | 0 | N/A | N/A | MEDIAN NOI TO FINAL DATE: | 725 | 24.1667 | 2.0139
[5 empty] | 25TH PERCENTILE | 211.75 | 7.0583 | 0.58014 | 25TH PERCENTILE | 143 | 4.7667 | 0.39178 | 25TH PERCENTILE | 62.25 | 2.075 | 0.17055 | 25TH PERCENTILE | 16.8667 | 1.3863 | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | 40 | 1.3333 | 0.10959 | 25TH PERCENTILE |  | 231 | 7.7 | 0.63288 | 25TH PERCENTILE |  | 26.5 | 0.88333 | 0.072603 | 25TH PERCENTILE |  | 538.5 | 17.95 | 1.4753 | 25TH PERCENTILE |  | N/A | N/A | N/A | 25TH PERCENTILE | 553 | 18.4333 | 1.5361
[5 empty] | 75TH PERCENTILE | 613.75 | 20.4583 | 1.6815 | 75TH PERCENTILE | 374.5 | 12.4833 | 1.026 | 75TH PERCENTILE | 120 | 4 | 0.32877 | 75TH PERCENTILE | 37.5083 | 3.0829 | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | 271 | 9.0333 | 0.74247 | 75TH PERCENTILE |  | 663.75 | 22.125 | 1.8185 | 75TH PERCENTILE |  | 596.75 | 19.8917 | 1.6349 | 75TH PERCENTILE |  | 1514 | 50.4667 | 4.1479 | 75TH PERCENTILE |  | N/A | N/A | N/A | 75TH PERCENTILE | 1232 | 41.0667 | 3.4222
Formulas:
NOI TO DEIS (DAYS) = DATEDIF([NEPA],[DEIS Date],"d")
DEIS TO FEIS NOA (DAYS) = DATEDIF([DEIS Date],[FEIS Date],"d")
FEIS TO ROD (DAYS) = DATEDIF([FEIS Date],[ROD Date],"d")
NOI TO ROD (DAYS) = DATEDIF([NEPA],[ROD Date],"d")
NOI TO ROD (YEARS) = (DATEDIF([NEPA],[ROD Date],"d"))/365
COMPLETION TIME (DAYS) = DATEDIF([Formal Consultation Initiated],[Conclusion of ESA Consultation],"d")
COMPLETION TIME (DAYS) = DATEDIF([SECTION 106],[Section 106 Concluded],"d")

## FAST-41 ONLY
PROJECT NAME* | LEAD AGENCY | PROJECT DESCRIPTION | PROJECT COST | NEPA | [15 empty] | NMFS EFH CONSULTATION |  |  |  |  | NMFS ESA CONSULTATION | [6 empty] | FWS ESA CONSULTATION | [6 empty] | SECTION 106 |  |  |  |  | USACE SECTION 10/404 |  |  |  |  | BLM RIGHT-OF-WAY |  |  |  |  | FS SPECIAL USE PERMIT |  |  |  |  | NOI TO COMPLETION OF FINAL ERA ACTION
|  |  |  | NOI Date | DEIS Date | NOI TO DEIS (DAYS) | NOI TO DEIS (MONTHS) | NOI TO DEIS (YEARS) | FEIS Date | DEIS TO FEIS NOA (DAYS) | DEIS TO FEIS NOA (MONTHS) | DEIS TO FEIS NOA (YEARS) | ROD Date | FEIS TO ROD (DAYS) | FEIS TO ROD (MONTHS) | FEIS TO ROD (YEARS) | NOI TO ROD (DAYS) | NOI TO ROD (MONTHS) | NOI TO ROD (YEARS) | Consultation Package Deemed Complete | Conclusion of EFH Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Formal Consultation Initiated | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Informal Consultation Initiated | Informal Consultation Concluded | Formal Consultation Initiated | Conclusion of ESA Consultation | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Consultation Initated with SHPO/THPO | Section 106 Concluded | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Pre-Construction Notification (PCN)/ Application Received | Final Verification/ Permit Decision Rendered | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Complete Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Completed Permit Application Received | Permit Approved | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS) | Last Approval Date | COMPLETION TIME (DAYS) | COMPLETION TIME (MONTHS) | COMPLETION TIME (YEARS)
Chokecherry and Sierra Madre Wind Energy Project | BLM | The project will develop a 1,000-turbine wind farm that will be able to generate up to 3,000 megawatts of electrictity and is located south of Sinclair and Rawlins in Carbon County, Wyoming | $5 billion | 2008-07-09 | 2011-07-22 | 1108 | 36.9333 | 3.0356 | 2012-06-29 | 343 | 11.4333 | 0.93973 | 2012-10-09 | 102 | 3.4 | 0.27945 | 1553 | 51.7667 | 4.2548 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-08-27 | 2012-09-05 | 9 | 0.3 | 0.024658 | 2008-07-25 | 2012-08-23 | 1490 | 49.6667 | 4.0822 | N/A | N/A | N/A | N/A | N/A | 2008-01-30 | 2012-10-09 | 1714 | 57.1333 | 4.6959 | N/A | N/A | N/A | N/A | N/A | 2012-10-09 | 1553 | 51.7667 | 4.2548
*Projects in bold were covered by FAST-41. | [5 empty] | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS |  | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  |  | DAYS | MONTHS | YEARS |  | DAYS | MONTHS | YEARS
[5 empty] | AVERAGE/ MEAN NOI TO DEIS: | 1108 | 36.9333 | 3.0356 | AVERAGE/ MEAN DEIS TO FEIS NOA: | 343 | 11.4333 | 0.93973 | AVERAGE/ MEAN FEIS TO ROD: | 102 | 3.4 | 0.27945 | AVERAGE/ MEAN NOI TO ROD: | 51.7667 | 4.2548 | AVERAGE/MEAN NMFS ESA CONSULTATION: |  | 0 | N/A | N/A |  |  | AVERAGE/MEAN NMFS ESA CONSULTATION: |  | 0 | N/A | N/A |  |  | AVERAGE/MEAN USFWS ESA CONSULTATION: |  | 9 | 0.3 | 0.024658 | AVERAGE/MEAN SECTION 106 CONSULTATION: |  | 1490 | 49.6667 | 4.0822 | AVERAGE/MEAN SECTION 10/404 REVIEW: |  | 0 | N/A | N/A | AVERAGE/MEAN BLM RIGHT-OF-WAY APPROVAL: |  | 1714 | 57.1333 | 4.6959 | AVERAGE/MEAN USFS SPECIAL USE PERMIT APPROVAL: |  | 0 | N/A | N/A | AVERAGE/ MEAN NOI TO FINAL DATE: | 1553 | 51.7667 | 4.3139
[5 empty] | MEDIAN NOI TO DEIS: | 1108 | 36.9333 | 3.0356 | MEDIAN DEIS TO FEIS NOA: | 343 | 11.4333 | 0.93973 | MEDIAN FEIS TO ROD: | 102 | 3.4 | 0.27945 | MEDIAN NOI TO ROD: | 51.7667 | 4.2548 | MEDIAN NMFS ESA CONSULTATION: |  | 0 | N/A | N/A |  |  | MEDIAN NMFS ESA CONSULTATION: |  | 0 | N/A | N/A |  |  | MEDIAN USFWS ESA CONSULTATION: |  | 9 | 0.3 | 0.024658 | MEDIAN SECTION 106 CONSULTATION: |  | 1490 | 49.6667 | 4.0822 | MEDIAN SECTION 10/404 REVIEW: |  | 0 | N/A | N/A | MEDIAN BLM RIGHT-OF-WAY APPROVAL: |  | 1714 | 57.1333 | 4.6959 | MEDIAN USFS SPECIAL USE PERMIT APPROVAL: |  | 0 | N/A | N/A | MEDIAN NOI TO FINAL DATE: | 1553 | 51.7667 | 4.3139
[5 empty] | 25TH PERCENTILE | N/A | N/A | N/A | 25TH PERCENTILE | N/A | N/A | N/A | 25TH PERCENTILE | N/A | N/A | N/A | 25TH PERCENTILE | N/A | N/A | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | N/A | N/A | N/A |  |  | 25TH PERCENTILE |  | N/A | N/A | N/A | 25TH PERCENTILE |  | N/A | N/A | N/A | 25TH PERCENTILE |  | N/A | N/A | N/A | 25TH PERCENTILE |  | N/A | N/A | N/A | 25TH PERCENTILE |  | N/A | N/A | N/A | 25TH PERCENTILE | N/A | N/A | N/A
[5 empty] | 75TH PERCENTILE | N/A | N/A | N/A | 75TH PERCENTILE | N/A | N/A | N/A | 75TH PERCENTILE | N/A | N/A | N/A | 75TH PERCENTILE | N/A | N/A | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | N/A | N/A | N/A |  |  | 75TH PERCENTILE |  | N/A | N/A | N/A | 75TH PERCENTILE |  | N/A | N/A | N/A | 75TH PERCENTILE |  | N/A | N/A | N/A | 75TH PERCENTILE |  | N/A | N/A | N/A | 75TH PERCENTILE |  | N/A | N/A | N/A | 75TH PERCENTILE | N/A | N/A | N/A
Formulas:
NOI TO DEIS (DAYS) = DATEDIF([NEPA],[DEIS Date],"d")
DEIS TO FEIS NOA (DAYS) = DATEDIF([DEIS Date],[FEIS Date],"d")
FEIS TO ROD (DAYS) = DATEDIF([FEIS Date],[ROD Date],"d")
NOI TO ROD (DAYS) = DATEDIF([NEPA],[ROD Date],"d")
NOI TO ROD (YEARS) = (DATEDIF([NEPA],[ROD Date],"d"))/365
COMPLETION TIME (DAYS) = DATEDIF([Formal Consultation Initiated],[Conclusion of ESA Consultation],"d")
COMPLETION TIME (DAYS) = DATEDIF([SECTION 106],[Section 106 Concluded],"d")